## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Saketh Vemula | 2025-12-05 | Missing values in user purchase history causing errors in user-item matrix | Milestone 1 (Weeks 1–2) | Self | Logical | Cleaned dataset and filled missing values | 2025-12-05 | Closed | User-item matrix ready for model training
2 | Saketh Vemula | 2025-12-16 | Recommendation model gives irrelevant suggestions for new users | Milestone 2 (Weeks 3–4) | Self | Logical | Added fallback logic for cold-start users | 2025-12-16 | Closed | Recommendations now relevant for new users
3 | Saketh Vemula | 2025-12-29 | Duplicate products appear in recommendation output | Milestone 3 (Weeks 5–6) | Self | Maintainability | Implemented duplicate filtering in output | 2025-12-29 | Closed | Recommendations are now unique
4 | Saketh Vemula | 2026-01-05 | Recommendation response time is slow on product page | Milestone 3 (Weeks 5–6) | Self | Standards | Optimized query and caching logic | 2026-01-05 | Closed | Response time reduced to <2 seconds
5 | Saketh Vemula | 2026-01-12 | Frontend integration shows errors while rendering suggestions | Milestone 4 (Weeks 7–8) | Self | Logical | Adjusted API response format and frontend code | 2026-01-12 | Closed | Recommendations display correctly

## Sheet2
Logical
User Interface
Maintainability
Standards
Others